## eHR Reqs list
Seq. | Req_ID | Requirement description | Mapping with Irish reqs | Objective | Category | MoSCoW | FUNC/ N-FUNC | Fase impl. | Date Impl. | Date testing | Doc. Github | Clinical WOFL ID | Comment | Acceptatie criteria / test
REQ01 | TSP1 | FHIR enabled services |  | Term. Services & Provisioning |  | Must | N-FUNC | 1. LTS | Q4/26 | Q3/27
REQ02 | TSP2 | ​​​Semantic definition and evaluation of SNOMED CT concept sets |  | Term. Services & Provisioning |  | Must | N-FUNC | 1. LTS | Q4/26 | Q3/27
REQ03 | TSP3 | Belgian Edition Release Currency |  | Term. Services & Provisioning | Versioning | Must | N-FUNC | 1. LTS | Q4/26 | Q3/27
REQ04 | TSP4 | Controlled SNOMED CT Release Deployment |  | Term. Services & Provisioning | Versioning | Must | N-FUNC | 1. LTS | Q4/26 | Q3/27
REQ05 | TSP5 | Version Consistency |  | Term. Services & Provisioning | Versioning | Must | N-FUNC | 2a - Problem | Q2/27 | Q3/27
REQ06 | TSP6 | Multilanguage accommodation |  | Term. Services & Provisioning | Maintenance | Must |  | 2a - Problem | Q2/27 | Q3/27
REQ07 | TSP7 | Provide a reporting/feedback mechanism |  | Term. Services & Provisioning | Versioning | Should |  | 2b.Patient Summary | Q2/28 | Q3/28
REQ08 | U01 | Overview of set of basic search functionalities |  | Data Entry | Term. Guidance | Must | FUNC | 2a - Problem | Q2/27 | Q3/27
REQ09 | U02 | The system will enable searches using Concept ID | SCT-017 The system will enable searches using Concept ID and Description ID. | Data Entry | Term. Guidance | Should | FUNC | 2b.Patient Summary | Q2/28 | Q3/28
REQ10 | U03 | Following the return of search results, the system will permit users to ​​browse through nearby hierarchy | SCT-020 Following the return of search results, the system will permit users to browse through IS A relationships | Data Entry | Term. Guidance | Should | FUNC | 2b.Patient Summary | Q2/28 | Q3/28
REQ11 | U04 | Limit searching and selection to only those concepts from SNOMED CT that have been specifically bound to that data element |  | Data Entry | Term. Guidance | Must | FUNC | 2a - Problem | Q2/27 | Q3/27
REQ12 | U05 | Allow data capture via free text when concepts cannot be found |  | Data Entry | Term. Guidance | Should | FUNC | 2b.Patient Summary | Q2/28 | Q3/28
REQ13 | U06 | Show user preferred display term for each SNOMED CT concept |  | Data Entry | User Interface | Should | FUNC | 2b.Patient Summary | Q2/28 | Q3/28
REQ14 | U07 | The eHR system shall display the most relevant concepts |  | Data Entry | User Interface | Should | FUNC | 2b.Patient Summary | Q2/28 | Q3/28
REQ15 | U08 | The eHR is capable of integrating tools/solutions facilitating the search and capture of clinical data |  | Data Entry | User Interface | Should | FUNC | 2b.Patient Summary | Q2/28 | Q3/28
REQ16 | S01 | The eHR must store SNOMED CT concept identifiers in the health records |  | Storage | Storage | Must | N-FUNC | 2a - Problem | Q2/27 | Q3/27
REQ17 | S02 | Ensure that the context of each SNOMED CT concept identifier or expression is clearly represented |  | Storage | Storage | Must | N-FUNC | 2a - Problem | Q2/27 | Q3/27
REQ18 | S03 | Active SNOMED CT concepts for data entry |  | Storage | Storage | Must | N-FUNC | 2a - Problem | Q2/27 | Q3/27
REQ19 | S04 | Preservation of historically coded data |  | Storage | Storage | Must | N-FUNC | 2a - Problem | Q2/27 | Q3/27
REQ20 | S05 | ​​​Use maps from SNOMED CT to national and international classifications including legacy and current data |  | Storage | Analytics and Reporting | Should | N-FUNC | 2b.Patient Summary | Q2/28 | Q3/28
REQ21 | S06 | Use SNOMED CT’s defining relationships in the determination of the correct results or outcomes |  | Storage | Analytics and Reporting | Should | N-FUNC | 2b.Patient Summary | Q2/28 | Q3/28
REQ22 | I01 | Use the national ​​exchange​​ standard FHIR to share data that are SNOMED CT coded in the eHR |  | Interoperability | Interoperability | Must | N-FUNC | 2a - Problem | Q2/27 | Q3/27
REQ23 | I02 | Reuse SNOMED CT coded data elements for all relevant message exchanges |  | Interoperability | Interoperability | Must | N-FUNC | 2a - Problem | Q2/27 | Q3/27

## dropdown coding
area Ierland | area eHR | area Belgium
Versiebeheer | Edition, Language and Content | Versioning
available content | User Interface | Language
data display | Analytics and Reporting | Content
search & select | Maintenance | User Interface
Reporting | Storage | Analytics and Reporting
post - coordination | Interoperability | Maintenance
interoperability | Additional Resources | Storage
historical data management |  | Interoperability
Search & select
MoSCoW | Must | Essentiële eisen zonder welke het project faalt of het product niet bruikbaar is.
| Should | Belangrijke, maar niet vitale eisen; moeten worden geïmplementeerd indien mogelijk
| Could | Wenselijke, "nice-to-have" functies die alleen worden uitgevoerd als er voldoende tijd en middelen zijn.
| Won't | Eisen die in deze fase niet worden meegenomen, maar wellicht in de toekomst.